Stage 1: Project Planning & Management

ML Diploma Graduation Project | Deliverable Template v1.0

| Team name | HexaMind |
| --- | --- |
| Project title | AI-Powered Predictive Maintenance System |
| Submission date | October 2026 |
| Version | v1 |

How to use this template

- Replace every [placeholder] and fill every table. If a section does not apply to your project, write why.

- Delete the gray guidance text before you submit.

- Keep the IDs you created in earlier stages (O-01, FR-01, T-01, TC-01). Later stages refer back to them.

- Save as TeamName_S1_ProjectPlan_v1.docx and send it to your instructor before the deadline of your track.

## 1. Project Summary

The AI-Powered Predictive Maintenance System is an end-to-end decision-support solution designed for mid-sized manufacturing plants to monitor machinery health and predict equipment failures. The system ingests and preprocesses time-series equipment sensor streams (vibration, temperature, and pressure) to forecast Remaining Useful Life (RUL) and detect anomalies using classical machine learning (XGBoost, Random Forest) and Deep Learning models (LSTM, GRU, 1D-CNN). It features an interactive Streamlit digital twin dashboard with what-if simulation capabilities and ROI cost savings calculation, Explainable AI (SHAP/LIME) modules for prediction transparency, a LangChain-backed LLM maintenance assistant with RAG grounding, and automated PDF diagnostic reporting. Operating strictly as a decision-support system without direct machine control, it empowers maintenance technicians, reliability engineers, shift operators, and plant managers to reduce unexpected downtime and optimize maintenance scheduling.

## 2. Team and Roles

| Member name | Email | Primary role | Main responsibilities |
| --- | --- | --- | --- |
| Salah Mohy Mohamed | salahmoheey5@gmail.com | Backend & Classical ML Lead | Backend architecture, XGBoost model training, MLflow experiment tracking, SHAP/LIME integration, and Streamlit simulator tools. |
| Youssef Mohamed Abdelrahman | youssef.m.moussa88@gmail.com | Time-Series Data & FastAPI Lead | Sensor feature engineering (FFT, rolling statistics), database schema design, and FastAPI inference service endpoints. |
| Jana Mohamed Fadly | janafadly05@gmail.com | Requirements & System Modeling Lead | Software Requirements Specification (SRS), UML behavioral and structural diagram package, DFDs, and integration coordination. |
| Zeyad Yasser Mahrous | almrawyzyad@gmail.com | Deep Learning & LLM/Automation Specialist | Deep learning RUL forecasting models (LSTM/GRU/1D-CNN), LangChain LLM assistant with guardrails/RAG, and automated PDF report generation. |
| Mariam Khaled Gamal | marimkhaled2006@gmail.com | UI/UX Frontend & Documentation Lead | Streamlit dashboard design, UI wireframing, QA test planning, end-user manual, and presentation materials. |
| Tasneem Ahmed Mohamed | tasneem200652@gmail.com | Data Analyst & Model Evaluator | Exploratory Data Analysis (EDA), signal correlation analysis, feature selection pipelines, and model performance metrics evaluation. |

## 3. Objectives and Success Criteria.

| ID | Objective | How it is measured | Target |
| --- | --- | --- | --- |
| O-01 | Accurate RUL Forecasting | Mean Absolute Error (MAE) and Root Mean Squared Error (RMSE) on held-out test dataset | MAE < 3.0 days, RMSE < 5.0 days across equipment test sequences |
| O-02 | Real-time Inference Latency | Execution latency of FastAPI inference pipeline per sensor batch | Model inference response time < 3.0 seconds under normal operating load (NFR-PERF-01) |
| O-03 | Interactive Dashboard Responsiveness | Fleet overview loading time and digital twin simulation rendering | Main fleet dashboard load time < 5.0 seconds (NFR-PERF-02) |
| O-04 | Operational Safety & Guardrails Compliance | Adherence to safety prompt restrictions and refusal of direct equipment control commands | 100% adherence to safety guardrails (0 direct machinery control commands executed) & local model fallback capability (NFR-SAFE-01, NFR-AVL-02) |

## 4. Scope

| In scope | Out of scope |
| --- | --- |
| Ingestion and validation of time-series sensor streams (vibration, temperature, pressure). | Direct write-back or physical control commands to PLCs, SCADA, or physical plant machinery (decision-support system only). |
| Signal preprocessing, Fast Fourier Transform (FFT) spectral analysis, and rolling feature extraction. | Direct live SCADA hardware connectivity (uses replayed sensor data stream). |
| Anomaly detection and RUL forecasting using classical ML (XGBoost, Random Forest) and Deep Learning (LSTM, GRU, 1D-CNN, Autoencoders). | Multi-tenant cloud subscription management or payment processing features. |
| Model evaluation (Precision, Recall, F1, ROC-AUC, MAE, RMSE) and MLflow experiment tracking/versioning. |  |
| Explainable AI (SHAP / LIME) feature importance visualizations for warning/critical alerts. |  |
| Streamlit digital twin dashboard featuring fleet status overview, time-series trend plotting, what-if simulator, and ROI cost calculator. |  |
| LangChain LLM Maintenance Assistant with context-aware RAG grounding and local model fallback. |  |
| Automated PDF maintenance diagnostic report generation (ReportLab / Jinja2). |  |

## 5. Work Breakdown Structure

| ID | Task | Owner | Start | End | Depends on |
| --- | --- | --- | --- | --- | --- |
| T-01 | Exploratory Data Analysis (EDA) & Sensor Distribution Analysis | Tasneem / Salah | Week 9 | Week 10 | None |
| T-02 | Backend API Specifications & Ingestion Schema Design | Youssef | Week 9 | Week 10 | None |
| T-03 | Requirements Gathering, Stakeholder Analysis & SRS Drafting | Jana | Week 9 | Week 10 | None |
| T-04 | LLM Prompt Specifications & PDF Report Template Design | Zeyad | Week 9 | Week 10 | None |
| T-05 | UI/UX Wireframes & Streamlit Dashboard Layout Prototype | Mariam | Week 9 | Week 10 | None |
| T-06 | Classical ML Training (XGBoost) & SHAP/LIME Module Integration | Salah | Week 13 | Week 16 | T-01 |
| T-07 | Time-Series Feature Engineering (FFT) & FastAPI Deployment | Youssef | Week 13 | Week 18 | T-02 |
| T-08 | Complete UML Diagram Package (Use Case, Sequence, Class) & DFDs | Jana | Week 13 | Week 15 | T-03 |
| T-09 | Deep Learning RUL Model Training (LSTM, GRU, 1D-CNN) | Zeyad | Week 14 | Week 18 | T-01, T-07 |
| T-10 | LangChain LLM Assistant Module & Automated PDF Generator | Zeyad | Week 15 | Week 19 | T-04, T-07 |
| T-11 | Interactive Streamlit Dashboard, What-If Simulator & ROI Calculator | Mariam / Salah | Week 14 | Week 19 | T-05, T-07 |
| T-12 | Model Evaluation, End-to-End Testing, Documentation & Final Presentation | All Team Members | Week 21 | Week 24 | T-06 to T-11 |

## 6. Milestones

| Milestone | Date | Deliverable | Owner |
| --- | --- | --- | --- |
| Stage 1: Project Planning & Management | Week 10 | This document | Team / Zeyad |
| Stage 2: Literature Review | Week 11 | Literature review document | Team / Zeyad |
| Stage 3: Requirements Gathering | Week 12 | Requirements document | Jana |
| Stage 4: System Analysis & Design | Week 13 | Design document | Jana / Salah |
| Internal: data pipeline complete | Week 15 | Feature Engineering & Ingestion Pipeline | Youssef / Tasneem |
| Internal: baseline model trained | Week 16 | XGBoost Baseline & MLflow Tracking | Salah |
| Internal: feature freeze | Week 20 | Codebase Freeze (Testing & Polish Only) | Team Lead |
| Stage 5: Implementation | Week 20 | Repository + implementation document | Team |
| Stage 6: Final presentation, testing & reports | Week 24 | Report, slides, demo | Team |

## 7. Tools and Collaboration

Give the instructor access to the repository and the task board.

| Purpose | Tool | Link |
| --- | --- | --- |
| Source code repository | GitHub | https://github.com/nhahub/NHA-5-173 |
| Task board | GitHub Projects | https://github.com/nhahub/NHA-5-173 |
| Shared documents | Google Drive / Google Docs | https://drive.google.com/drive/folders/1STtvubQwu-HnWSY1P8YvFv4IeRuGv_y5 |
| Team communication | WhatsApp / Discord | https://chat.whatsapp.com/D2IsosQpmzZHdWYDtduLPT?s=cl&p=i&mlu=0&ilr=4 |
| Experiment tracking (optional) |  |  |

## 8. Communication Plan

| Meeting or report | Frequency | Participants and purpose |
| --- | --- | --- |
| Team sync | Weekly | All team members; review WBS task progress, resolve technical blockers, and assign weekly goals. |
| Progress update to instructor | Bi-weekly | Team Lead & Course Instructor; present stage deliverables, review feedback, and align expectations. |
| Code review | Prior to PR Merge | Core developers (Salah, Youssef, Zeyad); ensure code quality, test coverage, and main branch stability. |

## 9. Risk Register

| Risk | Likelihood (L/M/H) | Impact (L/M/H) | Owner | Mitigation |
| --- | --- | --- | --- | --- |
| R-01: Data access / Lack of real failure dataset | M | H | Tasneem / Youssef | Utilize benchmark time-series datasets (ex: NASA C-MAPSS) and simulate degradation curves with synthetic noise. |
| R-02: Cloud LLM API downtime or privacy concerns | M | H | Zeyad | Implement automatic fallback to local open-source models (HuggingFace) and local-only execution mode (NFR-PRIV-02). |
| R-03: Model inference latency exceeding 3 seconds | L | H | Youssef / Zeyad | Optimize FastAPI pipeline, utilize model quantization/ONNX runtime, and pre-compute rolling features where applicable. |
| R-04: Integration delays between Streamlit UI & FastAPI | M | M | Salah / Mariam | Define OpenAPI/Swagger endpoints early and mock API responses during frontend development. |
| R-05: Team member capacity / availability issues | L | H | Team Lead | Maintain modular WBS tasks, clear documentation, and peer code reviews for seamless task handovers. |

## 10. Definition of Done

A project task is considered "Done" when:

- The code or deliverable is fully implemented and tested locally without unhandled errors.

- Code is pushed to GitHub and reviewed/approved by at least one other team member via Pull Request.

- Relevant technical documentation or inline docstrings are updated.

- Functionality is verified against system requirements (SRS/NFRs) and merged into the main branch.